## Sheet1
XXX Project Cost Estimate
Prepared by: | Date:
Note: Change the WBS items and other entries to meet your project needs. This data is from Figure 7-1 of Schwalbe's text
Information Technology Project Management, Fourth Edition. Also make sure the formulas work properly based on the data you enter.
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 306300 | 20.13%
1.1 Project manager | 960 | 100 | 96000
1.2 Project team members | 1920 | 75 | 144000
Contractors (10% of software development and testing) |  |  | 66300
2. Hardware |  |  |  | 76000 | 4.996%
2.1 Handheld devices | 100 | 600 | 60000
2.2 Servers | 4 | 4000 | 16000
3. Software |  |  |  | 614000 | 40.36%
3.1 Licensed software | 100 | 200 | 20000
3.2 Software development* |  |  | 594000
4. Testing (10% of total hardware and software costs) |  |  | 69000 | 69000 | 4.536%
5. Training and Support |  |  |  | 202400 | 13.3%
5.1 Trainee cost | 100 | 500 | 50000
5.2 Travel cost | 12 | 700 | 8400
5.3 Project team members | 1920 | 75 | 144000
6. Reserves (20% of total estimate) |  |  | 253540 | 253540 | 16.67%
Total project cost estimate |  |  |  | 1521240
* See software development estimate

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898